Activity Cost Estimates

Crypto Flux

Automated trading bot

Karachi, 75050

17th April 2026

Activity Cost Estimates: CryptoFlux (Release v1.0.0.0)

| WBS / Activity | Activity Description | Direct Costs (PKR) | Indirect Costs (PKR) | Contingency Reserves (15%) | Total Cost (PKR) | Basis of Estimate | Range (PKR) | Confidence Level |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Test Planning & Strategy Creation | 64,000 | 4,000 | 10,200 | 78,200 | Analogous (Test Manager @ 4,000/hr for 16 hrs) | 65,000 - 90,000 | High |
| 1.2 | Test Case Design (Auth, Market, Traders, News) | 100,000 | 4,000 | 15,600 | 119,600 | Parametric (Test Analyst @ 2,500/hr for 40 hrs) | 100,000 - 140,000 | High |
| 2.1 | QA Environment & DB Setup | 94,000 | 4,000 | 14,700 | 112,700 | Analogous (SysAdmin @ 2,000/hr + 70,000 AWS hosting) | 90,000 - 130,000 | Medium |
| 3.1 | Manual API & Integration Testing | 70,800 | 4,000 | 11,220 | 86,020 | Analogous (Tester @ 1,200/hr + 42,000 API License) | 75,000 - 100,000 | Medium |
| 3.2 | Manual UI & Exploratory Testing | 72,000 | 4,000 | 11,400 | 87,400 | Parametric (2 Testers @ 1,200/hr for 30 hrs each) | 70,000 - 110,000 | Medium |
| 4.1 | Defect Retesting & Regression Cycle | 38,400 | 4,000 | 6,360 | 48,760 | Parametric (Calculated using a 20% defect retest rate) | 35,000 - 70,000 | Low |
| 5.1 | Closure, Retrospective & Release Notes | 32,000 | 4,000 | 5,400 | 41,400 | Analogous (Test Manager @ 4,000/hr for 8 hrs) | 35,000 - 55,000 | High |

Breakdown of the 2025-2026 Estimations:

- Labor Rates (Current Market Averages): * Test Manager / QA Lead: ~PKR 4,000/hr

  - Senior SQA / Test Analyst: ~PKR 2,500/hr

  - Tester / Junior QA: ~PKR 1,200/hr

  - System Administrator: ~PKR 2,000/hr

- Direct Material Costs: International services (AWS staging server and the Sandbox Crypto API license) were converted from standard USD pricing into PKR (e.g., $250 USD estimated at ~PKR 70,000). These are bundled into the Direct Costs for activities 2.1 and 3.1.

- Indirect Costs: An overarching software license budget (for tools like Jira, Postman Pro, or test management suites) of about PKR 28,000/month was distributed evenly (PKR 4,000) across each activity to account for shared overhead.

- Contingency Reserves: Kept at a standard 15% to cover potential network downtime, scope creep during testing, or a higher-than-expected defect density.