## Activities
Phase | Activity | Description | Start Date | End Date | Duration (Weeks) | Dependencies | Milestone
1. Planning & Analysis | 1.1 Project Kick-off | Formal start of the project, defining team roles and initial objectives. | 2025-08-30 | 2025-09-01 | 1 |  | Yes
| 1.2 Requirements Gathering & Refinement | Deep dive into business and functional requirements with stakeholders. | 2025-09-04 | 2025-09-12 | 2 | 1.1 | No
| 1.3 Technical Architecture Design | Design the system architecture, including backend, frontend, and MT5 API integration. | 2025-09-09 | 2025-09-22 | 3 | 1.2 | Yes
| 1.4 Database Schema Design | Design the database for user management, trade history, and user settings. | 2025-09-24 | 2025-09-27 | 1 | 1.3 | Yes
| 1.5 Security & Compliance Plan | Outline security measures for user data and API keys. | 2025-09-24 | 2025-09-27 | 1 | 1.3, 1.4 | No
| 1.6 User Interface (UI) Mockups | Create wireframes and mockups for the frontend interface. | 2025-09-09 | 2025-09-17 | 2 | 1.2 | No
| 1.6 Feasibility Study | Evaluate technical and financial feasibility of the project. | 2025-09-29 | 2025-10-02 | 1 | 1.4 | No
| 1.7 Project Plan Approval | Obtain sign-off on project plan, scope, and resources. | 2025-10-05 | 2025-10-08 | 1 | 1.5 | Yes
2. Development & Integration | 2.1 User Management Backend | Develop APIs for user registration, login, and authentication. | 2025-09-29 | 2025-10-13 | 3 | 1.3, 1.4 | No
| 2.2 Bot Control Backend | Develop backend logic to start/stop the bot and manage its parameters. | 2025-09-29 | 2025-10-18 | 4 | 1.3, 2.1 | No
| 2.3 MT5 API Integration | Develop the Python-based service to interface with the MT5 terminal. | 2025-10-05 | 2025-10-23 | 4 | 1.3, C-1 | No
| 2.4 Market Data API Integration | Integrate with external APIs to fetch real-time crypto prices and news. | 2025-09-24 | 2025-10-08 | 3 | 1.3 | No
| 2.5 Frontend Development - User Management | Build the user account creation and login pages. | 2025-10-15 | 2025-10-23 | 2 | 1.6, 2.1 | No
| 2.6 Frontend Development - Bot Dashboard | Build the main user dashboard for bot control, market data, and trade history. | 2025-10-10 | 2025-11-02 | 5 | 1.6, 2.2, 2.4 | No
| 2.7 Trade History Module | Implement the backend and frontend to store and display trade history. | 2025-10-20 | 2025-11-02 | 3 | 2.2, 2.3 | No
| 2.8 Frontend Development | Develop the user interface based on approved designs. | 2025-10-10 | 2025-10-28 | 4 | 1.6 | No
| 2.9 Backend Development | Implement core business logic, APIs, and services. | 2025-10-10 | 2025-11-07 | 6 | 1.6 | No
| 2.10 System Integration | Integrate frontend, backend, and third-party services. | 2025-11-10 | 2025-11-23 | 3 | 2.1, 2.2 | Yes
3. Testing & QA | 3.1 Unit Testing | Test individual components and functions. | 2025-10-25 | 2025-11-02 | 2 | 2.1, 2.2, 2.3, 2.4 | No
| 3.2 Integration Testing | Test the end-to-end flow between frontend, backend, and MT5 API. | 2025-11-04 | 2025-11-18 | 3 | 3.1 | No
| 3.3 Performance Testing | Test for scalability and near-real-time data updates. | 2025-11-20 | 2025-11-23 | 1 | 3.2, NFR-1, NFR-4 | No
| 3.4 Security Audits | Conduct security tests to ensure data is stored securely. | 2025-11-25 | 2025-11-28 | 1 | 3.2, NFR-3 | No
| 3.5 Unit Testing | Test individual modules for functionality and reliability. | 2025-11-25 | 2025-12-03 | 2 | 2.2 | No
| 3.6 System Testing | Perform end-to-end system testing to ensure integration success. | 2025-12-05 | 2025-12-14 | 2 | 2.3 | No
| 3.7 User Acceptance Testing (UAT) | Validate the system with business stakeholders. | 2025-12-16 | 2025-12-24 | 2 | 3.2 | Yes
4. Deployment & Maintenance | 4.1 Production Environment Setup | Configure the server for deployment. | 2025-11-30 | 2025-12-03 | 1 |  | No
| 4.2 Initial Deployment | Deploy the bot and frontend to the production environment. | 2025-12-05 | 2025-12-08 | 1 | 4.1 | No
| 4.3 User Training & Documentation | Create user manuals and tutorials. | 2025-12-05 | 2025-12-14 | 2 | 2.6 | No
| 4.4 Ongoing Monitoring & Maintenance | Set up monitoring tools for performance and availability. | 2025-12-16 | 2025-12-16 | 2 | 4.2 | No
| 4.5 Deployment Preparation | Prepare deployment scripts, rollback plan, and infrastructure setup. | 2025-12-26 | 2025-12-29 | 1 | 3.3 | No
| 4.6 Production Go-Live | Deploy the system into production and verify critical functions. | 2025-12-31 | 2026-01-03 | 1 | 4.1 | Yes
| 4.7 Post-Deployment Support | Provide hypercare and monitor system performance. | 2026-01-05 | 2026-01-13 | 2 | 4.2 | No
| 4.8 Ongoing Maintenance | Handle bug fixes, enhancements, and regular updates. | 2026-01-16 | 2026-03-30 | 14 | 4.3 | No