## Activities
Phase | Activity | Description | Start Date | End Date | Duration (Weeks) | Dependencies
1. Planning & Analysis
| 1.1 Project Kick-off | Formal start of the project, defining team roles and initial objectives. | 2025-09-15 | 2025-09-19 | 1 | N/A
| 1.2 Requirements Gathering & Refinement | Deep dive into business and functional requirements with stakeholders. | 2025-09-22 | 2025-10-03 | 2 | 1.1
| 1.3 Technical Architecture Design | Design the system architecture, including backend, frontend, and MT5 API integration. | 2025-09-29 | 2025-10-17 | 3 | 1.2
| 1.4 Database Schema Design | Design the database for user management, trade history, and user settings. | 2025-10-20 | 2025-10-24 | 1 | 1.3
| 1.5 Security & Compliance Plan | Outline security measures for user data and API keys. | 2025-10-20 | 2025-10-24 | 1 | 1.3, 1.4
| 1.6 User Interface (UI) Mockups | Create wireframes and mockups for the frontend interface. | 2025-09-29 | 2025-10-10 | 2 | 1.2
2. Development & Integration
| 2.1 User Management Backend | Develop APIs for user registration, login, and authentication. | 2025-10-27 | 2025-11-14 | 3 | 1.3, 1.4
| 2.2 Bot Control Backend | Develop backend logic to start/stop the bot and manage its parameters. | 2025-10-27 | 2025-11-21 | 4 | 1.3, 2.1
| 2.3 MT5 API Integration | Develop the Python-based service to interface with the MT5 terminal. | 2025-11-03 | 2025-11-28 | 4 | 1.3, C-1
| 2.4 Market Data API Integration | Integrate with external APIs to fetch real-time crypto prices and news. | 2025-10-20 | 2025-11-07 | 3 | 1.3
| 2.5 Frontend Development - User Management | Build the user account creation and login pages. | 2025-11-17 | 2025-11-28 | 2 | 1.6, 2.1
| 2.6 Frontend Development - Bot Dashboard | Build the main user dashboard for bot control, market data, and trade history. | 2025-11-10 | 2025-12-12 | 5 | 1.6, 2.2, 2.4
| 2.7 Trade History Module | Implement the backend and frontend to store and display trade history. | 2025-11-24 | 2025-12-12 | 3 | 2.2, 2.3
3. Testing & Quality Assurance
| 3.1 Unit Testing | Test individual components and functions. | 2025-12-01 | 2025-12-12 | 2 | 2.1, 2.2, 2.3, 2.4
| 3.2 Integration Testing | Test the end-to-end flow between frontend, backend, and MT5 API. | 2025-12-15 | 2026-01-02 | 3 | 3.1
| 3.3 Performance Testing | Test for scalability and near-real-time data updates. | 2026-01-05 | 2026-01-09 | 1 | 3.2, NFR-1, NFR-4
| 3.4 Security Audits | Conduct security tests to ensure data is stored securely. | 2026-01-12 | 2026-01-16 | 1 | 3.2, NFR-3
4. Deployment & Maintenance
| 4.1 Production Environment Setup | Configure the server for deployment. | 2026-01-19 | 2026-01-23 | 1 | N/A
| 4.2 Initial Deployment | Deploy the bot and frontend to the production environment. | 2026-01-26 | 2026-01-30 | 1 | 4.1
| 4.3 User Training & Documentation | Create user manuals and tutorials. | 2026-01-26 | 2026-02-06 | 2 | 2.6
| 4.4 Ongoing Monitoring & Maintenance | Set up monitoring tools for performance and availability. | 2026-02-09 | Ongoing | Ongoing | 4.2