## Sheet1
Description of Potential Risk | Description of Potential Impact | Mitigation Plan | Contingency Plan | Monitoring Frequency | Likelihood (1-5) | Impact (1-5) | Controls (1-3) | Risk Rating | Category | Priority
MT5 API changes | Bot may stop functioning, leading to downtime and user dissatisfaction. | Monitor MT5 release notes & forums; Build API wrapper; Quarterly compatibility tests | Roll back to previous stable version, apply hotfix. | Monthly | 3 | 4 | 2 | 24 | Strategic | Medium
Regulatory changes in crypto trading | Loss of ability to trade in certain markets, potential legal exposure. | Engage legal experts; Restrict bot availability in high-risk jurisdictions | Restrict service in impacted regions until compliant. | Quarterly | 3 | 5 | 2 | 30 | Compliance | High
Security breach / user data leak | Financial and reputational loss, user trust collapse. | Encryption; Penetration testing; Security audits | Disable affected accounts, trigger incident response, notify users. | Continuous + Annual Audit | 2 | 5 | 1 | 10 | Operational | Low
Performance degradation under heavy load | System slows down or fails during peak usage. | Stress testing; Scalable cloud infrastructure | Temporarily restrict new signups, increase server capacity. | Before each major release | 3 | 3 | 2 | 18 | Operational | Medium
User adoption slower than expected | Revenue shortfall, delays in scaling. | Targeted marketing; Free demo/trials | Adjust strategy with referral bonuses or promotions. | Monthly | 3 | 3 | 2 | 18 | Financial | Medium
Bot makes consistent trading losses for users | Negative reviews, churn, reputational damage. | Disclaimers; Demo mode; Transparent risk warnings | Provide users disclaimers + manual stop option. | Continuous user feedback | 4 | 4 | 2 | 32 | Reputational | High
External Broker Dependency | Bot may fail if broker server goes down. | Monitor broker server status, alert users on downtime. | Switch Bots to demo account mode or pause until MT5 is restored. | Continuous | 2 | 4 | 2 | 16 | External Dependency | High
Trading Logic Failure | Incorrect trades leading to financial loss. | Rigorous QA testing of strategy logic, sandbox testing before launch. | Provide users disclaimers + manual stop option. | Pre-Release | 3 | 4 | 2 | 24 | Functional | Critical
Governance Failure | Unauthorized access or misuse of bot. | Code reviews, access control, GitHub/GitLab with audit trails. | Disable compromised module, pursue legal action if needed. | Quarterly | 2 | 5 | 1 | 10 | Security & Governance | High
News Feed Failure | Users may not get updated news, lowering trust. | Use multiple news feed providers, implement caching. | Temporarily disable news feature, inform users. | Monthly | 2 | 3 | 2 | 12 | Technical (News Feed) | Medium
Poor Usability | Users may abandon bot due to bad UX. | Conduct usability testing with novice traders, apply responsive design principles. | Release UI fixes in hotpatch update. | Quarterly | 3 | 3 | 2 | 18 | Usability | Medium