## Sheet1
Risk No | Description of Potential Risk | Description of Potential Impact | Risk Owner | Steps to Mitigate | Monitoring Frequency | Likelihood (1-5) | Impact (1-5) | Controls (1-3) | Risk Rating | Risk Category | Risk Level
S1 | MT5 API changes | Bot may stop functioning, leading to downtime and user dissatisfaction. | Development Team Lead | Monitor MT5 release notes & forums; Build API wrapper; Quarterly compatibility tests | Monthly | 3 | 4 | 2 | 24 | Strategic | Medium (Yellow)
C1 | Regulatory changes in crypto trading | Loss of ability to trade in certain markets, potential legal exposure. | Product Owner / Compliance Officer | Engage legal experts; Restrict bot availability in high-risk jurisdictions | Quarterly | 3 | 5 | 2 | 30 | Compliance | High (Red)
O1 | Security breach / user data leak | Financial and reputational loss, user trust collapse. | Security Lead | Encryption; Penetration testing; Security audits | Continuous + Annual Audit | 2 | 5 | 1 | 10 | Operational | Low (Green)
O2 | Performance degradation under heavy load | System slows down or fails during peak usage. | DevOps Lead | Stress testing; Scalable cloud infrastructure | Before each major release | 3 | 3 | 2 | 18 | Operational | Medium (Yellow)
F1 | User adoption slower than expected | Revenue shortfall, delays in scaling. | Product Owner | Targeted marketing; Free demo/trials | Monthly | 3 | 3 | 2 | 18 | Financial | Medium (Yellow)
R1 | Bot makes consistent trading losses for users | Negative reviews, churn, reputational damage. | Product Owner / Strategy Team | Disclaimers; Demo mode; Transparent risk warnings | Continuous user feedback | 4 | 4 | 2 | 32 | Reputational | High (Red)